Harlyn Primary School SDP 2015-16 - Overview

| SDP Targets for the whole year and term by term priorities | RAG Evaluation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Autumn |  | Spring |  | Summer |  |
|  | outcome | outcome | outcome | outcome | outcome | outcome |
| Area for improvement 1: By July 2016 To raise the achievement of groups of children and learners. - Higher attaining pupils in Maths and Reading - SEND in Phonics, Reading and Maths - White working class boys. |  |  |  |  |  |  |
| Autumn Term: Planning scrutiny/ Pupil Progress meetings / Forest School Planning /Needs Analysis |  |  |  |  |  |  |
| Spring Term: Formal observations / progress from last term (data)/ Target ‘outdoor learning’ opportunities |  |  |  |  |  |  |
| Summer Term: Data analysis of HA children and end of year attainment / Review impact of interventions and their outcomes |  |  |  |  |  |  |
| Area for improvement 2: By July 2016 To develop the effectiveness and capacity of the Senior Management Team. |  |  |  |  |  |  |
| Autumn Term: Weekly monitoring by Phase Leaders /Termly Phase Meeting. |  |  |  |  |  |  |
| Spring Term: Leadership Development CPD programme. |  |  |  |  |  |  |
| Summer Term: Evaluate the impact of SMT on School improvement over the year. |  |  |  |  |  |  |
| Area for improvement 3: By July 2016 To increase outcomes in Maths in line with progress in English. |  |  |  |  |  |  |
| Autumn Term: Review the teaching of Maths from Y2 in ability groups/classes. |  |  |  |  |  |  |
| Spring Term: Increase ‘interventions’ in Maths and cross-curricular opportunities. |  |  |  |  |  |  |
| Summer Term: Compare the two subject’s outcomes and progress. |  |  |  |  |  |  |
| Area for improvement 4: By July 2016 To continue to embed and refine the ‘post levels’ school assessment system. |  |  |  |  |  |  |
| Autumn Term: Ensure all staff are familiar with the system and previous assessments. |  |  |  |  |  |  |
| Spring Term: Assess child and analyse progress from the Autumn. (Plan accordingly) |  |  |  |  |  |  |
| Summer Term: Analyse the year’s progress and embed foundation subject assessments. |  |  |  |  |  |  |